## Sheet1
Project Name | Dynamic View Playbook
Project Start | 2026-02-02
Current Date | 2026-03-25
Weeks in Progress | 8
|  | In Progress | Completed | Planned
[7 empty] | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | May
[7 empty] | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31
Activity | Assigned To | Start | End | Days | Status | % Completed | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26
Phase 1- Identify | bar: 2026-02-06; 2026-07-31
Model - Scoping | Bhavya J | 2026-02-02 | 2026-02-13 | 11 | Completed | 100%
EXL & Competitors | Neha T | 2026-02-02 | 2026-02-20 | 18 | Completed | 100%
Client Info Sources | Bhavya J | 2026-02-02 | 2026-02-27 | 25 | In-Progress | 100%
Partners | Bhavya J | 2026-02-02 | 2026-02-27 | 25 | In-Progress | 50%
Phase 2: Planning
Scheduling | Bhavya J | 2026-02-02 | 2026-02-18 | 16 | Completed | 100%
Budgeting | Sushant K | 2026-02-02 | 2026-02-18 | 16 | Completed | 100%
Resource Plan | Sushant K/Bhavya J | 2026-02-02 | 2026-02-18 | 16 | Completed | 100%
Quality Planning | Bhavya J | 2026-02-16 | 2026-02-27 | 11 | In-Progress | 60%
Execution Sign-Off | Sushant K | 2026-02-02 | 2026-02-18 | 16 | Completed | 100%
Phase 3 - Execution
Playbook + Exec Alumni | Bhavya J | 2026-02-16 | 2026-02-27 | 11 | In-Progress | 70%
Competitors + Market Intel | Bhavya J | 2026-03-02 | 2026-03-16 | 14 | Planned
Partners | Bhavya J | 2026-03-17 | 2026-03-31 | 14 | Planned
Phase 4 - Closure
Documentation | Bhavya J | 2026-04-01 | 2026-04-15 | 14 | Planned
Feedbacks Incorporated | Bhavya J | 2026-04-01 | 2026-04-15 | 14 | Planned
Achievement Assessed | Sushant K/Bhavya J | 2026-04-01 | 2026-04-15 | 14 | Planned
Final Project Closed | Bhavya J | 2026-04-01 | 2026-04-15 | 14 | Planned